## Sheet1
Audio Commissioining Checklist
Version: | June 2024
Project:
Tech:
Date:
Step | Item | Status
PRE | Verify room is ready for configuration
PRE-A | Confirm DSP file has been reviewed
PRE-A.1 | Routes make sense
PRE-A.2 | AEC Reference is correct
PRE-A.3 | Adequate audio management available along the signal paths
PRE-B | Take acoustical measurements of the room to confirm assumptions.
PRE-B.1 | Take RT60 and NC of the room for performance prediction.
PRE-B.2 | Take STC of the room, if divisible and/or if privacy is a concern.
1 | Confirm the physical layout and installation of the audio system.
1.A | Loudspeakers
1.A.1 | Zones make sense, installed as designed.
1.A.2 | Loudspeakers are tapped correctly.
1.A.3 | Loudspeakers/logos are oriented the same direction in the room
1.B | Micronphones
1.B.1 | Wired properly, physically located as designed.
1.B.2 | Ceiling microphones are oriented the same direction in the room (Logos to front)
1.B.3 | Microphone arrays location/orientation in software matches physical location perfectly, as do table and talker locations
2 | Set listen levels
2.A | Play pink noise out of the loudspeaker zones at 0 dBu from the output
2.B | Adjust amplifiers to reach nominal listen levels in the room (65 dBA)
3 | Set EQ of the loudspeakers
3.A | Play pink noise at listen levels
3.B | Adjust EQ on the output of the system for a relatively flat (or preferred) response curve using an Real Time Analyzer
3.C | Paramteric EQ may be the easiest/smoothese way to approach this
3.D | In small rooms, you can do one loudspeakers and apply to all others as a good starting point.
4 | Set levels on microphones.
4.A | Wired microphones
4.A.1 | Use standard talker (60 dB @ 1m) to measure 0 dBu at the mixer input
4.B | Wireless microphones
4.B.1 | Set input levels at receiver, use standard talker (60 dB @ 1m) to set "nominal" level with no peaking at Lombard levels (70 dB @ 1m)
4.B.2 | Then set that output level with standard talker to 0 dBu at the mixer
4.B.3 | Set nominal program sources (-10 dBu) to 0 dBu at the mixer
5 | Set EQ on the microphones.
5.A | Start with known-good EQ curve from template file (e.g. - Linkwist-Riley)
5.A.1 | and/or roll off harshly (48 dB/octave) at 8k
5.A.2 | and/or roll off easily (12 dB/octave) at 250 Hz
5.B | Ring out/mix minus microphones for stability (if not unconditionally stable)
5.B.1 | Excite room by crowding the microphone, use the RTA to find unstable frequencies, and notch them out in the DSP
5.B.2 | Do not notch them out more than 6 dB per unstable frequency
5.B.3 | If room still rings, adjust gain of microphone (downstream of the pre-gain to the mixer at 0 dBu if possible)
5.B.4 | If more than five filters are required to improve stability, simply drop the overall gain of the microphone.
6 | Set program levels in the room
6.A | Use nominal sources to send -10 dBu pink noise into the system.
6.B | Adjust gain to (65 dBA) in the room as a nominal listen level
7 | Test conferencing levels
7.A | Confirm far end (Rx) has a listen level of 65 dBA in the room
7.B | Confirm near end (Tx) and far end (Rx) levels are measuring 0 dB at the mixer. (Note: Balancing Tx and Rx levels are crucial for good double talk performance.)
7.C | Confirm the AEC Reference is properly built and is 0 dBu
7.C.1 | AEC Reference should have all audio that needs to be cancelled from "that" microphone (far end, program, other microphones)
7.C.2 | ERL/ERLE should be optimized to confirm good AEC operation
7.C.3 | Confirm AEC Ref Level matches System Mic Levels with standard talker (RMLR = 0 dB)
7.D | Confirm no echo is heard.
7.D.1 | Confirm system has good double talk (full duplex operation).
7.D.2 | Only apply NLP conservatively, as this will affect double talk performance.
8 | Test conference program levels
8.A | Near end shared program sources should provide a 65 dBA listen level.
8.B | Far end shared program sources should provide a 65 dBA listen level.
9 | Confirm any and all presets are functioning in the site file.
10 | Demonstrate the performance of the system to the user, and confirm expectations have been met.